Process for RUE Committee

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Process Step** | ➊GATHER DATAResearch | ➋DEFINE | ➌GENERATE IDEAS | ➍REFINE | ➎BUILD | ➏PILOT |
| **Goal** | Understand needs of stakeholders | Define objectives for undergrad. Ed. | Identify ways of accomplishing objectives. | Evaluate ideas and select best ones for further development. | Develop specific undergrad experiences. | Test experiences and gather data |
| **Time (wks)** | 8 | 4 | 4 | 8 | 8-? | 2019-20 |
| **Tasks** | - Get info from:StudentsAlumniFacultyAdministrationEmployersState (USHE, Legislature)Other institutions(Surveys, panels, focus groups etc.)- Previously published research- Identify important constraints. Institutional(student demographics, facilities, personnel, costs, commuter campus, etc.) USHE | - State problems with current system.- Identify opportunities for improvement.- What undergrad. Ed. should do. | - Current ideas: FYE Seminar HIPs Degree Pathways- Other institutions- Conferences- Papers- Unique ideas | - Identify method for applying constraints and explore feasibility- Systematically review ideas  | - Create framework- Develop curriculum- Determine budget- Identify stewardship- Audience/subjects | - Gather necessary approvals(administration, grants, curriculum etc.) - Run pilot tests of experiences- Collect data- Analyze and assess results- Refine- Iterate |
| **Outcome/ Deliverables** | - Report including summary of methods, data collected, results and conclusions for each stakeholder group.- Process description for how to collect data. | - Report and presentation of  |  |  | - Proposal containing blueprint and framework for piloting. |  |
| **Audience/ Review/ Approval** |  |  |  |  |  |  |